## Gantt Chart
ONLINE QUIZ APP GANTT CHART
PROJECT TITLE |  | ONLINE QUIZ APPLICATION |  |  |  |  | DATE | [6 empty] | 2022-10-10
WBS REFERENCE | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION (DAYS) | PCT OF TASK COMPLETE | SPRINT ONE | [14 empty] | SPRINT TWO | [14 empty] | SPRINT THREE | [14 empty] | SPRINT 4
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
D | Project Vision | Arghawan S. | 2022-09-09 | 2022-10-02 | 23 | 100% | bar: WEEK 1 F to WEEK 4 M; WEEK 5 M
B | Personas and User Stories | Emanuel K. | 2022-09-09 | 2022-10-02 | 23 | 100% | bar: WEEK 1 F to WEEK 4 M; WEEK 5 M
A | Project Summary | Joyce B. | 2022-09-09 | 2022-10-02 | 23 | 100% | bar: WEEK 1 F to WEEK 4 M; WEEK 5 M
C | High-Level Requirements | James T. | 2022-09-09 | 2022-10-02 | 23 | 100% | bar: WEEK 1 F to WEEK 4 M; WEEK 5 M
E | Product Backlog | James T. | 2022-10-02 | 2022-10-10 | 8 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 4 M to WEEK 5 M
F | Team Charter | Arghawan S. | 2022-10-02 | 2022-10-10 | 8 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 4 M to WEEK 5 M
G | Project Plan | Joyce B. | 2022-10-02 | 2022-10-10 | 8 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 4 M to WEEK 5 M
H | Minutes of Meeting | James T. | 2022-09-09 | 2023-03-31 | 202 | 10%